| Consultancy | LRD Application Requirements | Fee |
| --- | --- | --- |
| CWPA Planning | - LRD Application fee. | Residential €130 per unit x 120 units; €15, 600.. Non – residential uses €7.20 per sqm.; €4137.12. Total; €19737.12. |
| CWPA Planning | - LRD Planning Application Form. |  |
| CWPA Planning | - Part V validation letter from FCC Housing Department. |  |
| CWPA Planning | - Copy of Site Notice (s). |  |
| CWPA Planning | - Original copy of the Newspaper Notice. |  |
| CWPA Planning | - One CD containing electronic copies of all the submitted planning application documentation as displayed on the applicant’s website (www.XXXlrd.ie). |  |
| CWPA Planning | - Statement of Response to FCC LRD Opinion. |  |
| CWPA Planning | - Planning Report & Statement of Consistency. |  |
| CWPA Planning | - Community & Social infrastructure Audit. |  |
| CWPA Planning | - Visual Impact Assessment. |  |
| CWPA Planning | - EIA Screening |  |
| CWPA Architecture | - Architectural Drawings / Plans and accompanying Drawing Schedule. |  |
| CWPA Architecture | - Overall Schedule of Accommodation and Areas. |  |
| CWPA Architecture | - Part V submission. |  |
| CWPA Architecture | - Building Life Cycle Report. |  |
| CWPA Architecture | - Universal Access Statement. |  |
| CWPA Architecture | - Materials Strategy in response to LRD Opinion. |  |
| CWPA Architecture | - Architectural & Urban Design Statement. |  |
| CWPA Architecture | - Housing Quality Assessment. |  |
| Moylan’s | - Engineering drawings, plans, schedule and associated reports (Water Services and Transportation). - Irish Water Agreement. New submission as previous was 6 months old. - Response to LRD Opinion. | Consultant dealing directly with Client. |
| RMDA Landscape Architects | - Landscape drawings, plans, schedule and associated reports (Water Services and Transportation). - Integrated Green Infrastructure Plan. | Consultant dealing directly with Client. |
| Charles McCorkell Arborist | - Arboricultural Assessment. | €1,300 ex VAT. |
| Mitchell Engineering | - AA Screening. | €1,100 ex VAT. |
| Digital Dimensions. | - Revised Daylight/ Sunlight Report. | Consultant dealing directly with Client. |
| i ACOUSTIS | - Noise Impacts. | €3,500 ex VAT. |
| Sabre | - Lighting Design. | €350 ex VAT. |
| Site Notices Ireland | - Site notice (s). | €250 ex VAT. |
| Matrix Internet | Website Preparation. | Approx. €2,200 ex VAT. |
| B-Fluid Ltd. | Micro-climate/ wind impacts. | € 7,900 (excl. VAT) |
| Archaeology and Heritage Consultancy | Archaeological Assessment and Method Statement. | € 1325 (excl. VAT and plant hire) |
| M & E Consultant | Climate Action Energy Statement. |  |
| Traffico | Road Safety Audit. | €2, 350 ex VAT. |

| Planning Considerations |  |  |  |
| --- | --- | --- | --- |
| LRD Application Requirement | Consultant | Update | Completion Date |
| Visual Impact Statement, impact on skyline and further visual impact on approach from west towards the coast. | CWPA. | To be prepared. | Nov 4th . |
| Daylight/ Sunlight Assessment – Within proposed development/ private and shared open spaces/ public areas and adjacent properties. | Digital Dimensions. | Report to be revised to include proposed development and impact on future occupiers. John Healy has confirmed this is required for planning as standard. Some rooms may not meet standards requiring design amendments. Expectation is to meet both Brith and Irish standards 100 % for all units. | Nov 10th . |
| Micro-climate/ wind impacts | AWN. | Email received with timeframe. | December 5th . |
| Noise impacts | AWN. | Email received with timeframe. | December 5th / Nov 14th . |
| Insufficient justification for private café at ground floor level. No parking provided. | Moylans |  |  |
| EIA & AA Screening | ESC Environmental | ESC Update. | November 4th . |
| Archaeology | Archaeological Assessment. | Amendments to report based on revised design. | November 10th . |
| Arborist? | TBC?? | Tree removal proposed along northern boundary. €550 ex VAT – Charles McCorkell. | TBC. |
| Architectural and Design Considerations |  |  |  |
| Materials Strategy | CWPA to prepare. Requirement for consistency with RMDA rationale report/ Moylan’s reports etc? NB. ** More considered approach to landscaping at upper floor areas noting coastal location of site. | CWPA to prepare. Shyamalima. | Nov 4th . |
| Building Life Cycle Report | CWPA – CC Draft example for Shyamalima. | Shyamalima to prepare. | Nov 4th . |
| Integrated Green Infrastructure Plan | RMDA. | RMDA to prepare. Specific requirements set out in LRD opinion. | Nov 4th . |
| Transportation Considerations |  |  |  |
| - Vehicular crossing of public footpath to give priority to pedestrians and cyclists crossing entrance. Requirement to consider layout of entrance taking into account NTA document? - Further detail on proposed setback along Myrtle Road. - Café/ gym/ yoga – No paring justification. - Car and bicycle parking provision justification. - Pedestrian entrance to the south to be provided. - EV Chargin points in accordance with Dev Plan. - Basement car park design standards IStructE. - Revised TTA taking account of Junction assessment with R809. - Stage 1 Road Safety Audit to be submitted. | Implications for frozen site plan? Requirement for alignment between CWPA/ RMDA/ Moylan’s in terms of site plan. |  | Nov 4th . |
| Water Services |  |  |  |
| - Surface water from the basement to be pumped to the foul network. - A pre-connection query requirement. - Surface water design acceptable. Requirement to adhere to Transport and Parks requirements re surface water. - Water supply connection from IW is acceptable. |  |  | TBC. |
| Housing Requirements |  |  |  |
| Part V proposal to be submitted for review in advance of lodgement. 20% requirement. No studios to be provided. 10% social 10% affordable. | Requirement to action as priority. Requirement to lodge prior to lodgement of official LRD. Seamus. |  |  |
| Lightning – Sabre. | Not sure if quote obtained to date? |  |  |

| November 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
|  |  | 1 | 2 | 3 | 4 | 5 |
| 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| 27 | 28 | 29 | 30 | 31 Aramex Planning App. |  |  |

November

Richmond Avene ABP Response.

McCrudden, Bollard and MCC Appeals.

Kay Cashen Enforcement.

Cathy Coghlan – Rush Enforcement.

Emma McGlynn/ Chris Tonge.

Aramex Planning Application.

LYNAS – 1 day.

MR Concrete.

Baldoyle LRD.

| December 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
|  |  |  |  | 1 | 2 | 3 |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 | 13 | 14 | 15 Baldoyle LRD | 16 | 17 |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 | 27 | 28 | 29 | 30 | 31 |

December

Joey & Claire Collins

Francis Hand

Vivian Hartford FI.

Manorlands Pre Planning/ Ostan Planning Application/ Leixlip Pre-Planning.

‘LRD floor space’, in relation to a building or part of a building, means the area ascertained by the internal measurement of the floor space on each floor of a building or part of a building (including internal walls and partitions), disregarding any floor space provided for—

(a) the parking of vehicles by persons—

(i) occupying or using the building or the part of the building,

(ii) for a purpose incidental to the primary purpose of the building or part of the building,

and

(b) ancillary residential services, including gyms and child-care facilities;